## Stakeholder Register
ArthaBank – Digital Loan Processing System
Stakeholder Register ¦ Prepared by: Joga Sai Vineeth ¦ Project: Vehicle Loan Processing System ¦ Date: June 2026
ID | Stakeholder Name | Role / Title | Type | Interest in Project | Influence Level | Impact on Project | Communication Method | Communication Frequency | Key Concerns / Expectations | Notes
S01 | Loan Applicant | Customer / End User | External | Apply for vehicle loan online without visiting branch | Low | High – primary user of the system | SMS, Email, In-app notifications | As needed / event-driven | Easy application process, fast approval, real-time status updates | Largest user group; UX is critical
S02 | Loan Officer | Bank Employee – Loan Processing | Internal | Process loan applications quickly and efficiently | Medium | High – reviews and approves all applications | Weekly team meetings, system dashboard | Weekly | Clear application dashboard, document validation, easy approval workflow | Identified by Vineeth in stakeholder analysis
S03 | Branch Manager | Head of Branch Operations | Internal | Ensure loans are approved efficiently and SLAs are met | High | High – oversees entire loan operations | Weekly status meetings, monthly MIS reports | Weekly | TAT (Turnaround Time) reduction, team productivity, compliance | Identified by Vineeth in stakeholder analysis
S04 | IT / Development Team | Software Developers | Internal | Receive clear and detailed functional requirements for development | High | High – builds and maintains the system | Sprint meetings, Jira tickets, Confluence docs | Daily (Agile standups) | Clear BRD/FRD, no ambiguous requirements, timely feedback | Works directly with BA on FRD and User Stories
S05 | QA / Testing Team | Quality Assurance Engineers | Internal | Ensure system works as per requirements before go-live | Medium | High – validates system against acceptance criteria | Sprint review meetings, RTM, UAT sign-off | Per sprint | Clear acceptance criteria, RTM coverage, UAT test cases | Identified by Vineeth in stakeholder analysis
S06 | Cybersecurity Team | Information Security & Compliance | Internal | Ensure customer data is protected and RBI guidelines are followed | Medium | High – approves security architecture | Security review meetings, compliance reports | Monthly / per release | Data encryption, access control, audit logs, VAPT compliance | Identified by Vineeth in stakeholder analysis
S07 | Reserve Bank of India (RBI) | Banking Regulator | External – Regulatory | Ensure bank complies with lending regulations and data protection laws | High | High – non-compliance can halt operations | Regulatory circulars, compliance reports | As per RBI guidelines | KYC compliance, fair lending practices, data privacy (DPDP Act) | Key external regulator for all banking systems in India
S08 | Vehicle Dealer | External Business Partner | External | Receive loan disbursement directly into dealer account from ArthaBank | Low | Medium – affected by disbursement process | Email notifications, bank transfer confirmations | Per transaction | Fast and accurate disbursement, transparent communication | Loan amount is transferred to dealer, not directly to applicant

## Legend
Influence Level Legend
High | Directly controls project decisions or budget
Medium | Involved in project but doesn't control decisions
Low | Affected by project outcome but no control