## Business Case
ARTHABANK – DIGITAL LOAN PROCESSING SYSTEM
Business Case Document ¦ Prepared by: Joga Sai Vineeth ¦ June 2026
A. PROJECT INFORMATION
| Project Name | ArthaBank Digital Loan Processing System
| Project Sponsor | Chief Digital Officer (CDO), ArthaBank
| Business Analyst | Joga Sai Vineeth – BA Trainee, Switch2ITJobs (SIT)
| Date | June 2026
| Version | 1.0
| Domain | Banking & Financial Services
B. PROBLEM STATEMENT — Why does this project exist?
ID | Problem | Description |  | Severity
P1 | Long Processing Time | Manual loan approval takes 7–14 business days causing customer frustration and drop-offs |  | High
P2 | Mandatory Branch Visits | Customers must visit branch in person for every loan application — inconvenient and time-consuming |  | High
P3 | Document Errors | Manual document collection leads to frequent errors, missing papers, and rework by loan officers |  | High
P4 | Zero Customer Visibility | Applicants have no way to track their application status — resulting in high call volumes to branch |  | Medium
P5 | Competitive Disadvantage | HDFC Bank and ICICI Bank already offer fully digital loan journeys — ArthaBank is losing customers |  | High
P6 | Scalability Issue | Manual process cannot scale — more loan applications require proportionally more staff |  | Medium
C. PROPOSED SOLUTION
ID | Feature | Description |  | Phase
F1 | Online Loan Application | Customers apply for Vehicle, Education, Personal loans online — no branch visit required |  | Phase 1
F2 | Document Upload & Validation | Digital document submission with automated checklist validation and status tracking |  | Phase 1
F3 | Real-Time Status Tracker | Customers track application progress via SMS, email, and in-app notifications |  | Phase 1
F4 | Officer Approval Dashboard | Loan officers review, approve/reject applications through a centralized dashboard |  | Phase 1
F5 | Auto Loan Disbursement | Automated transfer of approved loan amount to dealer/applicant account |  | Phase 2
F6 | Advanced MIS Reporting | Analytics dashboards for management on loan volumes, TAT, and officer performance |  | Phase 2
D. COST–BENEFIT ANALYSIS (High Level Estimate)
Category | Item |  | Estimated Value | Type
COST | System Development & Testing |  | ₹ 25–35 Lakhs | One-time
COST | Infrastructure & Cloud Hosting |  | ₹ 5–8 Lakhs/year | Recurring
COST | Training & Change Management |  | ₹ 2–3 Lakhs | One-time
BENEFIT | Increased Loan Applications (40% growth) |  | ₹ 50+ Lakhs/year | Revenue
BENEFIT | Reduced Branch Operational Cost |  | ₹ 10–15 Lakhs/year | Savings
BENEFIT | Reduced Document Rework & Errors |  | ₹ 3–5 Lakhs/year | Savings

## Project Charter
PROJECT CHARTER — ArthaBank Digital Loan Processing System
Prepared by: Joga Sai Vineeth ¦ Switch2ITJobs (SIT) ¦ Version 1.0 ¦ June 2026
1. PROJECT OVERVIEW
Project Name | ArthaBank Digital Loan Processing System
Project Sponsor | Chief Digital Officer (CDO), ArthaBank
Business Analyst | Joga Sai Vineeth – BA Trainee, Switch2ITJobs (SIT)
Project Manager | TBD – Assigned by ArthaBank IT PMO
Start Date | July 2026
Target Go-Live | October 2026 (Phase 1)
Budget (Estimated) | ₹ 30–45 Lakhs (Phase 1)
2. PROJECT OBJECTIVE
To build a Digital Loan Processing System that enables ArthaBank customers to apply for loans online, upload documents digitally, track application status in real-time, and receive decisions through an Officer Approval Dashboard — eliminating manual branch visits and reducing loan TAT from 14 days to under 3 days.
3. SCOPE
Scope Type | Item
IN SCOPE | Online Loan Application Form (Vehicle, Education, Personal)
IN SCOPE | Digital Document Upload & Automated Validation
IN SCOPE | Real-Time Application Status Tracker
IN SCOPE | Loan Officer Approval Dashboard
OUT OF SCOPE | Automatic Loan Disbursement (Phase 2)
OUT OF SCOPE | Advanced MIS Reporting & Analytics (Phase 2)
OUT OF SCOPE | Mobile App Development (Phase 2)
OUT OF SCOPE | Core Banking System Integration (Phase 2)
4. KEY RISKS & MITIGATION
ID | Risk Description | Severity | Mitigation Strategy
R1 | Resistance from branch staff to adopt digital process | High | Change management training & phased rollout
R2 | Data security & RBI compliance concerns | High | Engage cybersecurity team early; conduct VAPT before go-live
R3 | Low digital literacy among rural loan applicants | Medium | Provide helpline support and branch-assisted digital onboarding
R4 | Delay in third-party integrations (SMS/Email gateway) | Medium | Finalize vendors in Month 1; have fallback manual notification
R5 | Scope creep due to stakeholder change requests | Medium | Strict change control process; BA to manage RTM and scope log
5. KEY STAKEHOLDERS
Stakeholder | Type | Role in Project
Loan Applicant | External | Primary end user of the system
Loan Officer | Internal | Reviews and approves loan applications
Branch Manager | Internal | Oversees operations and approves project decisions
IT / Dev Team | Internal | Builds and maintains the system
QA Team | Internal | Tests and validates system against requirements
Cybersecurity Team | Internal | Ensures data protection and RBI compliance
Reserve Bank of India | Regulatory | External regulator — KYC and lending guidelines
Vehicle Dealer | External | Receives loan disbursement; impacted by process
6. PROJECT APPROVAL & SIGN-OFF
Prepared By | Joga Sai Vineeth | BA Trainee – SIT | June 2026
Reviewed By | SIT Trainer | Business Analyst Coach | June 2026
Approved By | Chief Digital Officer | ArthaBank | June 2026