## User Stories
ARTHABANK – USER STORIES WITH ACCEPTANCE CRITERIA
Digital Vehicle Loan Processing System ¦ Prepared by: Joga Sai Vineeth ¦ Switch2ITJobs (SIT) ¦ June 2026
Story ID | Feature | User Story (As a... I want... So that...) | Priority | Sprint | Story Points | Acceptance Criteria | Status | Notes
US-001 | Registration | As a Loan Applicant, I want to register on ArthaBank portal with my name, mobile, and email, So that I can access the loan application system | Must Have | Sprint 1 | 3 | 1. Registration requires Full Name, Mobile, Email 2. OTP sent to mobile within 60 seconds 3. OTP valid for 5 minutes 4. Duplicate mobile shows error message 5. Password min 8 chars, 1 uppercase, 1 number | To Do | Identified by trainee
US-002 | Login | As a Loan Applicant, I want to login using mobile number and OTP, So that my account is secure and I don't need to remember a password | Must Have | Sprint 1 | 2 | 1. Login via mobile + OTP only 2. OTP delivered within 60 seconds 3. Max 3 wrong OTP attempts before 15-min lockout 4. Unregistered mobile shows 'Please sign up' message | To Do | OTP login — as specified in FRD
US-003 | Loan Application | As a Loan Applicant, I want to apply for a vehicle loan online by filling personal, vehicle, and loan details, So that I can buy my vehicle without visiting the branch | Must Have | Sprint 1 | 5 | 1. Form captures: Name, DOB, PAN, Aadhaar, Address, Employment, Income 2. Vehicle fields: Type, Brand, Model, Cost, Dealer name 3. Loan fields: Amount, Tenure (12/24/36/48/60 months) 4. EMI auto-calculated on amount + tenure selection 5. Unique reference number generated on submission 6. Confirmation SMS + email within 2 minutes | To Do | Core feature — must have
US-004 | Document Upload | As a Loan Applicant, I want to upload my KYC and financial documents digitally, So that I don't need to submit physical documents at the branch | Must Have | Sprint 1 | 5 | 1. Accepted formats: PDF, JPG, PNG only 2. Max file size: 10MB per document 3. Wrong format shows re-upload option with error message 4. Document checklist shows uploaded/pending/missing status 5. System sends reminder if docs incomplete after 24 hours | To Do | Applicant identified file formats in session
US-005 | Status Tracking | As a Loan Applicant, I want to track my loan application status in real-time online, So that I don't need to call the branch for updates | Must Have | Sprint 2 | 3 | 1. Status stages: Submitted → Docs Verified → Under Review → Decision → Disbursed 2. Each stage shows timestamp 3. SMS + email sent within 5 minutes of every status change 4. If 'More Info Required' — reason shown with re-upload option | To Do | As specified by trainee in FRD
US-006 | Notifications | As a Loan Applicant, I want to receive SMS and email alerts at every stage of my application, So that I stay informed without logging in repeatedly | Must Have | Sprint 2 | 2 | 1. Notifications sent at: submission, doc upload, under review, approved/rejected, disbursed 2. Both SMS and email channels 3. Delivered within 5 minutes of trigger 4. All notifications stored in profile history | To Do | 5-minute SLA — trainee specified
US-007 | Officer Dashboard | As a Loan Officer, I want to view all pending loan applications in a centralized dashboard, So that I can efficiently review and process them without missing any | Must Have | Sprint 2 | 5 | 1. Dashboard shows: App ID, Applicant Name, Loan Amount, Type, Date, Status 2. Filter by loan type, date, status, amount 3. Summary cards: Total, Pending, Approved Today, Rejected Today 4. Click any application to view full details + documents | To Do | Officer identified in stakeholder analysis
US-008 | Approval Decision | As a Loan Officer, I want to approve or reject loan applications with documented reasoning, So that decisions are transparent and communicated to applicants | Must Have | Sprint 2 | 5 | 1. Options: Approve / Reject / Request More Info 2. Rejection reason is MANDATORY 3. Dropdown reasons: Low Credit Score / Insufficient Income / Incomplete Docs / Other (free text) 4. Customer auto-notified within 5 minutes 5. All decisions logged with officer ID + timestamp | To Do | Trainee specified mandatory reason + dropdown + Other
US-009 | Disbursement | As a Loan Applicant, I want to receive a digital loan sanction letter and have the amount disbursed to the dealer, So that I can collect my vehicle without any manual paperwork | Should Have | Sprint 3 | 5 | 1. Sanction letter auto-generated with: amount, rate, tenure, EMI 2. Amount disbursed to dealer bank account (not applicant) 3. Applicant receives SMS + email on disbursement 4. Loan account number generated post-disbursement | To Do | Money to dealer — trainee identified this
US-010 | EMI Schedule | As a Loan Applicant, I want to view my complete EMI repayment schedule, So that I can plan my finances and never miss a payment | Could Have | Sprint 3 | 3 | 1. EMI schedule shows: EMI no., due date, amount, principal, interest, balance 2. Upcoming EMI highlighted on dashboard 3. Reminder sent 5 days before due date 4. Payment history shows paid/unpaid EMIs 5. Late payment penalty shown on missed EMI | To Do | Phase 1 — basic schedule view

## Product Backlog
ARTHABANK – PRODUCT BACKLOG
Digital Vehicle Loan Processing System ¦ Prepared by: Joga Sai Vineeth ¦ June 2026
Backlog ID | Story ID | Feature | Description | Priority | Story Points | Sprint | Status | MoSCoW
PB-001 | US-001 | Registration | Customer registration with OTP verification | Must Have | 3 | Sprint 1 | To Do | Must Have
PB-002 | US-002 | Login | Secure OTP-based login system | Must Have | 2 | Sprint 1 | To Do | Must Have
PB-003 | US-003 | Loan Application | Online vehicle loan application form with EMI calculator | Must Have | 5 | Sprint 1 | To Do | Must Have
PB-004 | US-004 | Document Upload | Digital KYC document upload with auto-validation | Must Have | 5 | Sprint 1 | To Do | Must Have
PB-005 | US-005 | Status Tracker | Real-time application status tracker with timeline | Must Have | 3 | Sprint 2 | To Do | Must Have
PB-006 | US-006 | Notifications | Automated SMS + email notifications at every stage | Must Have | 2 | Sprint 2 | To Do | Must Have
PB-007 | US-007 | Officer Dashboard | Centralized dashboard for loan officer to review applications | Must Have | 5 | Sprint 2 | To Do | Must Have
PB-008 | US-008 | Approval Decision | Approve / Reject with mandatory reason and audit log | Must Have | 5 | Sprint 2 | To Do | Must Have
PB-009 | US-009 | Disbursement | Digital sanction letter + auto disbursement to dealer | Should Have | 5 | Sprint 3 | To Do | Should Have
PB-010 | US-010 | EMI Schedule | EMI repayment schedule with reminders | Could Have | 3 | Sprint 3 | To Do | Could Have
PB-011 | — | Branch Manager | Branch Manager monitoring dashboard and reports | Should Have | 4 | Sprint 3 | To Do | Should Have
PB-012 | — | Security | Data encryption, VAPT, RBI compliance audit | Must Have | 5 | Sprint 1 | To Do | Must Have
BACKLOG SUMMARY
Sprint | Stories | Total Points | Features Covered | Goal
Sprint 1 | 4 | 15 | Registration, Login, Loan Application, Document Upload | Core loan application experience — customer can apply and upload docs
Sprint 2 | 4 | 15 | Status Tracker, Notifications, Officer Dashboard, Approval | Complete review and approval workflow — officer can process applications
Sprint 3 | 4 | 17 | Disbursement, EMI Schedule, Manager Dashboard, Security | Disbursement, repayment, and management reporting

## Sprint Plan
ARTHABANK – SPRINT PLAN
Digital Vehicle Loan Processing System ¦ 3 Sprints × 2 Weeks ¦ Prepared by: Joga Sai Vineeth ¦ June 2026
Sprint | Story ID | Feature | Task Description | Assignee | Est. Days | Status | Definition of Done
Sprint 1 | US-001 | Registration | Build customer registration form with OTP validation | Dev Team | 3 | To Do | OTP delivered, duplicate check works, all validations pass
Sprint 1 | US-002 | Login | Build OTP-based login with lockout after 3 failures | Dev Team | 2 | To Do | Login works, lockout triggers after 3 attempts
Sprint 1 | US-003 | Loan Application | Build online loan application form with EMI calculator | Dev Team | 5 | To Do | Form submits, ref number generated, SMS/email sent
Sprint 1 | US-004 | Document Upload | Build document upload module with auto-validation | Dev Team | 5 | To Do | All 7 docs accepted, wrong format rejected, checklist shown
Sprint 1 | PB-012 | Security | Implement data encryption and basic security framework | Dev Team | 3 | To Do | HTTPS enforced, data encrypted at rest and in transit
Sprint 2 | US-005 | Status Tracker | Build real-time application status tracker with timeline | Dev Team | 3 | To Do | 5 stages shown, timestamps correct, status updates in real-time
Sprint 2 | US-006 | Notifications | Build automated SMS + email notification system | Dev Team | 2 | To Do | Notifications sent within 5 mins of trigger, all 7 stages covered
Sprint 2 | US-007 | Officer Dashboard | Build centralized officer dashboard with filters and stats | Dev Team | 5 | To Do | Dashboard loads, filters work, stats accurate, docs viewable
Sprint 2 | US-008 | Approval Decision | Build approval/rejection workflow with audit log | Dev Team | 5 | To Do | Rejection reason mandatory, customer notified, audit log stored
Sprint 3 | US-009 | Disbursement | Build digital sanction letter and disbursement to dealer | Dev Team | 5 | To Do | Letter generated, disbursement to dealer confirmed, customer notified
Sprint 3 | US-010 | EMI Schedule | Build EMI schedule view with payment reminders | Dev Team | 3 | To Do | EMI table shows all fields, reminders sent 5 days before due date
Sprint 3 | PB-011 | Manager Dashboard | Build branch manager monitoring dashboard | Dev Team | 4 | To Do | TAT metrics, officer performance, loan volume visible
SPRINT TIMELINE OVERVIEW
Sprint | Duration | Start | End | Stories | Points | Goal | Key Deliverable
Sprint 1 | 2 weeks | 01 Jul 2026 | 14 Jul 2026 | 5 | 18 | Customer can register, apply, and upload documents | Working loan application + document upload
Sprint 2 | 2 weeks | 15 Jul 2026 | 28 Jul 2026 | 4 | 15 | Officer can review, verify, and approve/reject loans | Complete approval workflow live
Sprint 3 | 2 weeks | 29 Jul 2026 | 11 Aug 2026 | 4 | 17 | Disbursement, EMI, and management dashboard complete | Full system ready for UAT